## Slide 1
Preparation of the Forest concession management PLAN (rku)
Pt. restoration ekosistem Indonesia
Patron’s Meeting 5-6 November 2025

## Slide 2
2.3. Work Area Arrangement based on Time/Block/Compartment (100%)
Work Area for HH area 10 years of work
Work Area HH area becomes working/patrol block
Work area smallest area of block
Forest Planning (50%)
Forest and Biodiversity Protection Plan
Rehabilitation and Restoration Plan
Forest Utilisation Plan and Business Development plan
Partnership and Cooperation Plan
Conflict Management Plan
Work Area Arrangement
2.1. Based on type management (100%)
Hutan Harapan Protected Area
Self-Managed Protection Area
Partnership Protection Area
Hutan Harapan Production Area
Self Managed Production Area
Partnership Production Area
Business Cooperation Production Area
PPKH Area
2.1. Based on Utilization (100%)
Area Utilisation
Environmental Service
NTFP Utilization
NTFP Collection
Tactical Plan
Based on Area and Time Management
Strategic Plan
Based on Land Use Management
Land Use Direction (100%)
Core Forest Area
Cultivation/ Rehabilitation area
Challenged Area
Annual Workplan and Budget (AWPB) based on agreed target and duties is in progress.
RKU dan RKT Draft have been discussed 50%
Operational Plan 2025 not yet ready 60%
Completed 100%
In Progress 75%
Operational Plan
In Progress 65%
Forestry Concession Management Plan Progress
Notes: Strategic Plan:
Tactical Plan: annual
Operational Plan: based on daily, weekly, and monthly

## Slide 3
Forestry Concession Management Progres
Land-use Management Direction (100%)
A
A
C
B
B
Work Area Arregement (100%)
Based on type management
Production Areas
24,325 ha
Protection Areas
73,689 ha
Based on utilization
Strategic Plan
Based on Land Use Management
Completed 100%
Strategic Plan
Based on Land Use Management

## Slide 4
Forestry Concession Management Plan Progress
Work Area Arrangement Based on time/block/ compartment
Draft Forest Planning Document UpToDate
Tactical Plan
Based on Area and Time Management
Output Annual
Result indicator
Forest Protection
Forest Utilization
Social
Company
Strategic Program
Component program
Integrated Program
10 Year Activities
Yearly Activities
Duties
Forest Planning Document (In Progress)
Forest and Biodiversity Protection Plan
Rehabilitation and Restoration Plan
Forest Utilization Plan and Business Development plan
Partnership and Cooperation Plan
Conflict Management Plan
Budget Structure
Draft RKUPH
Budget Needed

## Slide 5
RKUPH Revision Progress
Draft RKUPH Revision Completed
Operational Plan
Ten Year Plan (RKUPH) Progress
Draft Consultation with Ibu Listya completed in October 2025
Land Cover analysis and maps from appointed consultant (Completed)
Updating land cover data to the Work Area Arrangement (Completed)
Updating the Draft RKUPH (in Progress)
Internal meeting for the Draft Revised RKUPH for All Departments (Completed)
Informal meeting with Ministry of Forestry staff to review the draft and ensure completeness before moving on to the next stage (completed)hings
Based on the meeting with the ministry of forestry staff, we need to revised several items
Submission target/ 5 Nov 2025
Submission via online or hard copy depending on direction from Ministry of Forestry
An online process require validation of existing RKUPH that is currently underway in the system (SIPASHUT)

## Slide 6
Draft RKUPH Revision REKI Jambi and Sumsel
Draft RKUPH Revision Completed
Operational Plan : RKUPH Revision
Forestry Concession Management Plan Progress
A. General Data
Evaluation of the previous RKUPH Plan and Realization
Forest Utilization Business Work Plan
Company Identity
Investment Plan
Forest Conditions based on Forest Area Maps
Potential Data
Precondition Aspects
Production Aspects
Environmental Aspects
Social Aspects
Developed multi-business
Boundaries
Arrangement of Work Area