Board of Patron’s Rolling Action List

Colour description:

Done		    		In Progress			   No Progress

| Patron’s Meeting 12-13 November 2024 |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Item | Action Taken |  | Status |
| 1 | Action Point: (1) Revision of page 4 of the financial update presentation to include Franklinia in the list; (2) to add additional slide on the secured funding to date for YAKEHI and PT REKI and (3) to add information on all financial contributions made by RSPB, including those made to YAKEHI and Burung, not paid directly to PT REKI (e.g. hiring of consultants). | - Completed - Will be available for BoP meeting this month - Ongoing. |  | Done |
| 2 | Action Point: When completed, Land Use Management Plan to be sent to BOM for review before sending to Patrons for approval. | Plan has been approved by BoM, will be sent to BoP for final approval at Patron’s meeting 5-6 November 2026. |  |  |
| 3 | PT REKI to develop a financial report on the vanilla business for BoM to review; (ii) BoM to review the vanilla business after the KADIN project and possibly develop an exit strategy; (iii) PT REKI to request Ibu Nuning to provide contacts that can support fermentation for the vanilla pods that have been harvested. | Done. Ibu Nuning visited PT REKI in April 2024 to provide instruction on vanilla fermentation. PT REKI has developed a maintenance budget for the vanilla that has already been planted. An update will be provided at the 5-6 November Patron’s meeting. |  |  |
| 4 | Burung to make a cost estimate for a KBA assessment of Harapan | Ongoing |  |  |
| 5 | Action Points: (i) PT REKI to meet with the MoF to have the Ministry put pressure on PT MBJ; | Ongoing. Since December 2024, PT REKI has had numerous meetings with the Ministry of Forestry and South Sumatra provincial agencies to put pressure on the PT MBJ. |  |  |
| 6 | (ii) PT REKI to send a letter to MoF stating that PT MBJ is not respecting the agreement; | Done |  |  |
| 7 | (iii) PT REKI to continue strengthening its presence in the south. | Ongoing. An update will be presented at the 5-6 November Patron’s meeting |  |  |
| 8 | Action Point: Engage with the MoF about Jindi’s plans to determine the Ministry’s position. | - Ongoing. - Jindi will conduct 3D seismic survey activities beginning in October-November 2025. - An update will be presented at the 5-6 November Patron’s meeting |  |  |
| 9 | Action Point: Communications Protocol to be developed by BoM. | Draft Protocol is available |  |  |
| 10 | The 2024 audit report is to be completed in April 2025 for PT REKI and Yayasan KEHI. | In progress. Final edits are being made. May be available for the 5-6 November Patron’s meeting |  |  |
| 11 | Yayasan KEHI will send thank you letter to Pak Boedi Mranata. | Completed, 13 January 2025 |  |  |
| 12 | Action point: Legalize the meeting decision through updating the Yayasan KEHI deeds. | Completed. 13 December 2024 |  |  |
| BOARD OF PATRONS Meeting – 11 February 2025 |  |  |  |  |
| 13 | Board to check via email with Agus Sarsito on any reservations about the MoU with APRIL. | Done. Reported back in the 27 March Patron’s meeting |  |  |
| 14 | Harapan to have Communications Guidance ready ahead of the signing of the first MOU to anticipate questions or queries once the contract has been signed. | Done. Document is available |  |  |
| 15 | Financial report needs to clarify the carry-over from 2024. IEF and RSPB fundings are available. | Done. The financial reports were adjusted to reflect this |  |  |
| 16 | Board would like to compare last year’s and this year’s budget to be able to judge the status of the cashflow and want to understand the 2026 budget. | Done. Report back in the 27 March meeting. |  |  |
| 17 | Since APRIL’s USD500,000-grant is going to forest protection, the Board had asked BoM to provide recommendations for closing the gap. | Done. |  |  |
| 18 | BOM to provide recommended steps to cover for any financial gaps in 2025. | Done |  |  |
| 19 | YAKEHI Chair to provide 2025 Budget and 2026 Budget for Board of Patrons’ meeting on March 27, 0900 UK time/1600 WIB. | Done |  |  |
| 20 | BoP to make a decision whether to continue the vanilla business in the March meeting. | Done |  |  |
| BOARD OF PATRONS Meeting – 27 March 2025 |  |  |  |  |
| 21 | SK to contact Ernest and Young to advise on the tax issues, if necessary. SK to come back to the board if the tax to be deducted is a significant amount. | Done |  |  |
| 22 | Patrons asked SK to inform the Patrons of any significant issues arising from the negotiations with APRIL. | Done. |  |  |
| 23 | YAKEHI to check the YAKEHI Audit Report p.5 regarding the composition of Patrons in the audit reports and the dates. | Done. Audit report was adjusted to reflect this |  |  |
| 24 | TAW to check discrepancy in slides 3 and 6 of the presentation and update the Board on the assumption for the figures. | Done |  |  |
| 25 | Land Use Management Plan is to be discussed in the next Patron’s meeting, which is to be followed by a discussion on Harapan Business Plan (including vanilla). | Done |  |  |
| 26 | TAW to present the business options that could be pursued in a Patrons’ meeting on 12 May. | Done |  |  |
| 27 | BOM is asked to review activities and identify efficiencies and find other sources of funding. | Done |  |  |
| BOARD OF PATRONS Meeting – 12 May 2025 |  |  |  |  |
| 28 | Vina to inform Patrons when the 1st Agreement between APRIL and Harapan Partners was signed. | Done. |  |  |
| 29 | Shashi and Vina to present options for Plan B on funding for Harapan. | Done |  |  |
| 30 | Tom to provide Patrons with reworked 2025 Budget and 2026 Budget which address the gap between forecast and expenditure. | Done. |  |  |
| 31 | TAW to schedule the next Patrons meeting for July 10 to discuss the Land Use Management Plan, and if urgent can schedule an earlier time given than the topic is a priority. | Done. Separate discussions were held with Pak Agus S. regarding the land use plan. |  |  |
| BOARD OF PATRONS Meeting – 10 July 2025 |  |  |  |  |
| 32 | TAW/SK With regard to the Secondary Sales and Trust Fund to be set up, to seek advice on tax, the execution (incl. the period of mandatory announcement) and whether the members of BOD/BOC have to be Indonesian. | The BoP will be updated on this at the 5-6 November Patron’s meeting. |  |  |
| 33 | Harapan Partners to ensure the Communications Plan is ready before the announcement of the transfer of shares is made | Done |  |  |
| 34 | DNA (Dian Agista) to check when we need to inform the government regarding the transfer of shares | The BoP will be updated on this at the 5-6 November Patron’s meeting. |  |  |
| 35 | The Partners is to set up a discussion on guaranteeing forest standing in the collaboration with APRIL, which may need to be captured in a separate shareholders agreement and the role of the Partners in the collaboration. | The BoP will be updated on this at the 5-6 November Patron’s meeting. |  |  |
| 36 | TAW to check whether the operational cost to be carried over to 2026 can be used for different allocations. | The BoP will be updated on this at the 5-6 November Patron’s meeting. |  |  |
| 37 | Partners to look at carbon project design (as part of consideration for value of Harapan). | The BoP will be updated on this at the 5-6 November Patron’s meeting. |  |  |
| BOARD OF PATRONS Meeting – 5-6 November 2025 |  |  |  |  |
| 38 | TAW to circulate Grievance Mechanism to Patrons | Please refer to the link (Click Here) for the detail information of Grievance Report |  |  |
| 39 | The request on how to use the remaining funds of EUR 13,495 was approved, provided that the land and building tax for 2026 will be covered by PT REKI’s business and there will not need to be a drawdown from SIA or IEF | The land and building tax for 2026 will be covered by MBJ’s fund |  |  |
| 40 | Machmudy to clarify the discrepancy between Shashi’s figures and his figures | Please refer to the link (Click Here) for the clarification. |  |  |
| 41 | Finance team and BoM to prepare a contingency budget for July and perhaps longer just in case the transfer of shares does not take place as scheduled |  |  |  |
| 42 | In anticipation of a possible cashflow shortfall in January 2026, TAW and ES to prepare narrative and budget report for BLI regarding SIA activities so that the funds can be released in December 2025 | the fund form BLI SIA has been received in Yakehi account on 22 Januari 2026 |  |  |
| 43 | Ensure better patrolling across all Harapan grids and record in SMART; report back to Patrons |  |  |  |
| 44 | PT REKI management to investigate/ encourage others in Sumatra why honey production is down. |  |  |  |
| 45 | Serious Incident Reports to be made an agenda item in future Patron’s meetings | Please refere the link (Click Here) for serious incident report 2025 in HH |  |  |
| 46 | Provide data on the number of staff in the north and along the coal road | Nort Area Pos 49 : 5 staff Pos 52 : 7 staff Pos Mekala : 6 staf Total : 18 staff | Along the coal Road Fleet A and Fleet B : 11 staff Fleet C : 2 staff and Pos Sembilu : 10 staff |  |
| 47 | Include development of participating household numbers in Patron’s report | Please refer the link (Click Here) for Report of Community Livelihood Development of Hutan Harapan |  |  |
| 48 | Clarify timeline for developing the Second Agreement with APRIL to ensure clarity for all Harapan Partners |  |  |  |
| 49 | Pak Bambang to meet with Pak Anton this month regarding his shares | Done |  |  |
| 50 | In the agreement will APRIL, we should ensure that the greenbelts in HH are twice the regulation size. |  |  |  |
| 51 | Legalize the meeting decisions through updating the Yayasan KEHI deeds | Done |  |  |
| 52 | Legalize the meeting decision through updating the Articles of Association to the Ministry of Law and Human Rights for PT REKI | Still in the process of changing data in the Legal Administration system |  |  |